## Issues
Ticket ID | GH # | Title | Module | Epic | Priority | Phase | Size | Est. days | Cut | Area | Status | Assignees | State | Blocked by | Open blockers | Link
ADM-L01 | 205 | [ADMIN] Build the platform admin console | admin | [EPIC] M18 · Platform Admin & Billing | — | Later | L |  | Later | backend | Accepted |  | OPEN | IDN-006 |  | open
ADM-L02 | 206 | [ADMIN] Meter usage for billing | admin | [EPIC] M18 · Platform Admin & Billing | — | Later | M |  | Later | backend | Accepted |  | OPEN | OBS-004 |  | open
ADM-L03 | 207 | [ADMIN] Add subscriptions and customer invoicing | admin | [EPIC] M18 · Platform Admin & Billing | — | Later | L |  | Later | backend | Accepted |  | OPEN | ADM-L02 |  | open
AGT-001 | 132 | [AGENT] Build the LLM adapter with routing and timeouts | agent | [EPIC] M09 · AI Agent | P0 | M1 | M |  | A | ai | Assigned | therealtunguyen | OPEN | EXE-002 |  | open
AGT-002 | 134 | [AGENT] Log every AI call and fail closed | agent | [EPIC] M09 · AI Agent | P0 | M1 | S |  | A | ai | Assigned | therealtunguyen | OPEN | AGT-001 |  | open
AGT-003 | 133 | [AGENT] Implement untrusted-content wrapping and sanitization | agent | [EPIC] M09 · AI Agent | P0 | M1 | S |  | A | ai | Assigned | therealtunguyen | OPEN | AGT-001 |  | open
AGT-004 | 135 | [AGENT] Implement invoice extraction | agent | [EPIC] M09 · AI Agent | P0 | M1 | M |  | A | ai | Assigned | therealtunguyen | OPEN | AGT-003, AGT-002, INV-004 |  | open
AGT-005 | 170 | [AGENT] Extract and validate payment terms | agent | [EPIC] M09 · AI Agent | P0 | M1 | S |  | A | ai | Assigned | therealtunguyen | OPEN | AGT-004, ENG-005 |  | open
AGT-006 | 171 | [AGENT] Detect instruction-like text in documents | agent | [EPIC] M09 · AI Agent | P0 | M1 | S |  | A | ai | Assigned | therealtunguyen | OPEN | AGT-004 |  | open
AGT-007 | 143 | [AGENT] Implement the read-only tool layer | agent | [EPIC] M09 · AI Agent | P0 | M1 | M |  | A | ai | Assigned | therealtunguyen | OPEN | CHR-002, ENG-008, POL-003 |  | open
AGT-008 | 144 | [AGENT] Implement the plan proposer | agent | [EPIC] M09 · AI Agent | P0 | M1 | M |  | A | ai | Assigned | therealtunguyen | OPEN | AGT-007 |  | open
AGT-009 | 145 | [AGENT] Score AI proposals and select the plan | agent | [EPIC] M09 · AI Agent | P0 | M1 | S |  | A | ai | Assigned | therealtunguyen | OPEN | AGT-008, ENG-008 |  | open
AGT-010 | 172 | [AGENT] Implement rule-based fallback templates | agent | [EPIC] M09 · AI Agent | P0 | M1 | S |  | A | ai | Assigned | therealtunguyen | OPEN | ENG-007, POL-003 |  | open
AGT-011 | 173 | [AGENT] Draft exception requests with a numeric post-check | agent | [EPIC] M09 · AI Agent | P1 | M1 | S |  | B | ai | Assigned | therealtunguyen | OPEN | AGT-001, MDT-006 |  | open
AGT-012 | 174 | [AGENT] Build the Copilot backend | agent | [EPIC] M09 · AI Agent | P1 | M1 | L |  | After submission | ai | Assigned | therealtunguyen | OPEN | AGT-007 |  | open
AGT-013 | 176 | [AGENT] Build the extraction accuracy eval | agent | [EPIC] M09 · AI Agent | P0 | M1 | S |  | B | ai | Assigned | therealtunguyen | OPEN | AGT-005, DOM-004 |  | open
AGT-014 | 178 | [AGENT] Build the planner benchmark (B1 vs B2) | agent | [EPIC] M09 · AI Agent | P0 | M1 | M |  | A | ai | Assigned | therealtunguyen | OPEN | AGT-009, ENG-006, DOM-005 |  | open
AGT-015 | 180 | [AGENT] Build the red-team suite runner | agent | [EPIC] M09 · AI Agent | P0 | M1 | S |  | A | ai | Assigned | therealtunguyen | OPEN | AGT-006, DOM-006 |  | open
AGT-016 | 182 | [AGENT] Build the Copilot numeric-fidelity suite | agent | [EPIC] M09 · AI Agent | P1 | M1 | S |  | After submission | ai | Assigned | therealtunguyen | OPEN | AGT-012, DOM-007 |  | open
AGT-017 | 183 | [AGENT] Add a secondary LLM provider fallback | agent | [EPIC] M09 · AI Agent | P1 | M1 | M |  | After submission | ai | Assigned | therealtunguyen | OPEN | AGT-001 |  | open
AUD-001 | 54 | [AUDIT] Implement the hash-chained audit log | audit | [EPIC] M15 · Audit & Evidence | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | IDN-001 |  | open
AUD-002 | 197 | [AUDIT] Add audit read and chain verification | audit | [EPIC] M15 · Audit & Evidence | P0 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | AUD-001 |  | open
AUD-003 | 66 | [AUDIT] Define the evidence bundle schema and exporter | audit | [EPIC] M15 · Audit & Evidence | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | AUD-001, EXE-008 |  | open
AUD-004 | 198 | [AUDIT] Propagate coverage labels through the API | audit | [EPIC] M15 · Audit & Evidence | P1 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | CHR-002 |  | open
AUD-L01 | 199 | [AUDIT] Anchor the audit hash root on-chain daily | audit | [EPIC] M15 · Audit & Evidence | — | Later | S |  | Later | backend | Accepted |  | OPEN | AUD-002 |  | open
CHR-001 | 35 | [CHAIN] Build the RPC client with failover | chain-reader | [EPIC] M06 · Chain Reader & Tx Tracking | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | TRS-002 |  | open
CHR-002 | 140 | [CHAIN] Implement block-consistent snapshots | chain-reader | [EPIC] M06 · Chain Reader & Tx Tracking | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | CHR-001, TRS-004 |  | open
CHR-003 | 47 | [CHAIN] Implement the transaction tracker | chain-reader | [EPIC] M06 · Chain Reader & Tx Tracking | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | CHR-001, EXE-001 |  | open
CHR-004 | 141 | [CHAIN] Detect reorgs and re-evaluate status | chain-reader | [EPIC] M06 · Chain Reader & Tx Tracking | P1 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | CHR-003 |  | open
CHR-005 | 117 | [CHAIN] Index module and Safe events | chain-reader | [EPIC] M06 · Chain Reader & Tx Tracking | P1 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | CHR-001, SC-016 |  | open
CHR-006 | 253 | [CHAIN] Index treasury token movements and alert on unexpected outflows | chain-reader | [EPIC] M06 · Chain Reader & Tx Tracking | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | CHR-005, EXE-001 |  | open
CMP-001 | 50 | [COMPLIANCE] Build the screening adapter and fixture provider | compliance | [EPIC] M14 · Compliance | P1 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | MDT-001 |  | open
CMP-002 | 191 | [COMPLIANCE] Screen payees before each PAY | compliance | [EPIC] M14 · Compliance | P1 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | CMP-001, POL-003 |  | open
CMP-003 | 192 | [COMPLIANCE] Implement data classification, encryption helpers and log redaction | compliance | [EPIC] M14 · Compliance | P0 | M1 | M |  | B | backend | Assigned | Nostidus4 | OPEN | DEV-001 |  | open
CMP-L01 | 193 | [COMPLIANCE] Integrate a KYB provider | compliance | [EPIC] M14 · Compliance | — | Later | L |  | Later | backend | Accepted |  | OPEN | CMP-001 |  | open
CMP-L02 | 194 | [COMPLIANCE] Add Travel Rule support | compliance | [EPIC] M14 · Compliance | — | Later | L |  | Later | backend | Accepted |  | OPEN | CMP-L01 |  | open
CMP-L03 | 195 | [COMPLIANCE] Add retention and deletion workflows | compliance | [EPIC] M14 · Compliance | — | Later | M |  | Later | backend | Accepted |  | OPEN | CMP-003 |  | open
CMP-L04 | 196 | [COMPLIANCE] Add region pinning for stored data | compliance | [EPIC] M14 · Compliance | — | Later | M |  | Later | backend | Accepted |  | OPEN | CMP-L03 |  | open
DEV-001 | 21 | [DEVEX] Initialize monorepo skeleton | devex | [EPIC] M19 · Developer Experience & Quality | P0 | M1 | M |  | A | infrastructure | Done |  | CLOSED |  |  | open
DEV-002 | 22 | [DEVEX] Create Docker Compose stack (local profile) | devex | [EPIC] M19 · Developer Experience & Quality | P0 | M1 | M |  | A | infrastructure | Done |  | CLOSED | DEV-001 |  | open
DEV-003 | 23 | [DEVEX] Add CI workflow for Python | devex | [EPIC] M19 · Developer Experience & Quality | P1 | M1 | S |  | A | infrastructure | Done |  | CLOSED | DEV-001 |  | open
DEV-004 | 25 | [DEVEX] Add CI workflow for contracts | devex | [EPIC] M19 · Developer Experience & Quality | P1 | M1 | S |  | B | infrastructure | Assigned | therealtunguyen | OPEN | SC-001 |  | open
DEV-005 | 27 | [DEVEX] Add CI workflow for web and OpenAPI client drift | devex | [EPIC] M19 · Developer Experience & Quality | P1 | M1 | S |  | After submission | infrastructure | Done |  | CLOSED | WEB-001 |  | open
DEV-006 | 53 | [DEVEX] Write seed script for the local environment | devex | [EPIC] M19 · Developer Experience & Quality | P1 | M1 | M |  | A | infrastructure | Assigned | therealtunguyen | OPEN | SC-016, TRS-004, MDT-003, INV-003 |  | open
DEV-007 | 67 | [DEVEX] Build scenario runner CLI | devex | [EPIC] M19 · Developer Experience & Quality | P1 | M1 | M |  | A | infrastructure | Assigned | therealtunguyen | OPEN | DEV-006, AUD-003 |  | open
DEV-008 | 68 | [DEVEX] Write the demo runbook | devex | [EPIC] M19 · Developer Experience & Quality | P1 | M1 | S |  | A | infrastructure | Assigned | therealtunguyen | OPEN | DEV-007 |  | open
DEV-009 | 69 | [DEVEX] Build the reliability run harness | devex | [EPIC] M19 · Developer Experience & Quality | P1 | M1 | S |  | After submission | infrastructure | Assigned | therealtunguyen | OPEN | DEV-007 |  | open
DEV-010 | 71 | [DEVEX] Add testnet profile and VM deployment | devex | [EPIC] M19 · Developer Experience & Quality | P1 | M1 | M |  | A | infrastructure | Assigned | therealtunguyen | OPEN | DEV-002, DOM-001, SC-016 |  | open
DEV-011 | 72 | [DEVEX] Enforce module boundaries with import-linter | devex | [EPIC] M19 · Developer Experience & Quality | P1 | M1 | S |  | After submission | infrastructure | Done |  | CLOSED | DEV-001 |  | open
DEV-012 | 264 | [DEVEX] Add the deployment config gate to CI | devex | [EPIC] M19 · Developer Experience & Quality | P0 | M1 | S |  | A | infrastructure | Assigned | therealtunguyen | OPEN | SC-016, DEV-003 |  | open
DOM-001 | 70 | [DOMAIN] Verify Ethereum Sepolia infrastructure (owner: Phúc) | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | S |  | A | non-code | Ready for Assignment |  | OPEN |  |  | open
DOM-002 | 230 | [DOMAIN] Set up tUSDC and the Circle USDC evidence run (owner: Phúc) | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | S |  | A | non-code | Ready for Assignment |  | OPEN | DOM-001 |  | open
DOM-003 | 231 | [DOMAIN] Ask the organizers whether testnet evidence is accepted | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P1 | M1 | S |  | A | non-code | Ready for Assignment |  | OPEN |  |  | open
DOM-004 | 175 | [DOMAIN] Author the labelled invoice dataset (30) | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | M |  | B | non-code | Ready for Assignment |  | OPEN |  |  | open
DOM-005 | 177 | [DOMAIN] Author planner scenarios with ground truth (≥30) | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | L |  | A | non-code | Ready for Assignment |  | OPEN |  |  | open
DOM-006 | 179 | [DOMAIN] Author the red-team invoice set (20) | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | M |  | A | non-code | Ready for Assignment |  | OPEN |  |  | open
DOM-007 | 181 | [DOMAIN] Author Copilot question cases (20) | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P1 | M1 | S |  | After submission | non-code | Ready for Assignment |  | OPEN | DOM-005 |  | open
DOM-008 | 232 | [DOMAIN] Review business rules and demo limits from a finance view | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | S |  | A | non-code | Ready for Assignment |  | OPEN |  |  | open
DOM-009 | 233 | [DOMAIN] Review the threat model and write the known-risk list | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | M |  | A | non-code | Ready for Assignment |  | OPEN |  |  | open
DOM-010 | 234 | [DOMAIN] Run customer interviews (2–3) | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P1 | M1 | M |  | B | non-code | Ready for Assignment |  | OPEN |  |  | open
DOM-011 | 235 | [DOMAIN] Write the security self-assessment report | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | M |  | A | non-code | Ready for Assignment |  | OPEN | DOM-009, SC-015 |  | open
DOM-012 | 236 | [DOMAIN] Assemble the technical documentation for submission | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | M |  | A | non-code | Ready for Assignment |  | OPEN | DOM-011 |  | open
DOM-013 | 237 | [DOMAIN] Create the 10-minute presentation deck | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | M |  | A | non-code | Ready for Assignment |  | OPEN | DOM-008 |  | open
DOM-014 | 238 | [DOMAIN] Script and record the 5-minute demo video | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P0 | M1 | M |  | A | non-code | Ready for Assignment |  | OPEN | DEV-008 |  | open
DOM-015 | 239 | [DOMAIN] Write the compliance positioning note and license inventory | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P1 | M1 | S |  | B | non-code | Ready for Assignment |  | OPEN |  |  | open
DOM-016 | 240 | [DOMAIN] Update the FigJam board from the repo diagrams | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P2 | M1 | S |  | After submission | non-code | Ready for Assignment |  | OPEN |  |  | open
DOM-017 | 241 | [DOMAIN] Choose the repository license | domain-evidence | [EPIC] M20 · Domain & Evidence (non-code) | P1 | M1 | S |  | After submission | non-code | Ready for Assignment |  | OPEN |  |  | open
ENG-001 | 42 | [ENGINE] Create py-core money types and domain models | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | DEV-001 |  | open
ENG-002 | 92 | [ENGINE] Implement the liquidity calculator | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-001 |  | open
ENG-003 | 93 | [ENGINE] Implement the refill decision table | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-002 |  | open
ENG-004 | 94 | [ENGINE] Add property tests for buffer and limit safety | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | ENG-003 |  | open
ENG-005 | 95 | [ENGINE] Model payment terms and their value function | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-001 |  | open
ENG-006 | 96 | [ENGINE] Implement the baseline scheduler B1 (earliest deadline first) | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-003, ENG-005 |  | open
ENG-007 | 97 | [ENGINE] Implement the terms-aware scheduler with OR-Tools CP-SAT | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | L |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-006, ENG-012 |  | open
ENG-008 | 98 | [ENGINE] Expose plan scoring and binding-constraint reporting | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-007 |  | open
ENG-009 | 99 | [ENGINE] Implement invoice fingerprint normalization and hashing | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-001 |  | open
ENG-010 | 57 | [ENGINE] Build EIP-712 typed data for payment approvals and attestations | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | SC-017, ENG-001 |  | open
ENG-011 | 100 | [ENGINE] Implement the 7-day liquidity forecast | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P2 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | ENG-003 |  | open
ENG-012 | 243 | [ENGINE] Implement the exhaustive oracle scheduler for tests | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-006 |  | open
ENG-013 | 259 | [ENGINE] Implement reserve formulas and the liquidity decision | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-002, ENG-005 |  | open
ENG-014 | 260 | [ENGINE] Build the borrow proposal | financial-engine | [EPIC] M07 · Financial Engine (py-core) | P1 | M1 | S |  | B | backend | Assigned | Nostidus4 | OPEN | ENG-013 |  | open
ENG-L01 | 101 | [ENGINE] Plan refills from other operational wallets | financial-engine | [EPIC] M07 · Financial Engine (py-core) | — | Later | M |  | Later | backend | Accepted |  | OPEN | ENG-007, SC-L06 |  | open
ENG-L02 | 102 | [ENGINE] Add FX conversion and depeg checks for fiat invoices | financial-engine | [EPIC] M07 · Financial Engine (py-core) | — | Later | M |  | Later | backend | Accepted |  | OPEN | ENG-005 |  | open
ENG-L03 | 103 | [ENGINE] Extend the scheduler to multiple assets | financial-engine | [EPIC] M07 · Financial Engine (py-core) | — | Later | M |  | Later | backend | Accepted |  | OPEN | ENG-007 |  | open
EXE-001 | 46 | [EXECUTION] Create operations (outbox), transactions and gas ledger schema | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | INV-001 |  | open
EXE-002 | 131 | [EXECUTION] Set up Celery with core and ai queues | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | DEV-002 |  | open
EXE-003 | 142 | [EXECUTION] Implement the deadline trigger | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | EXE-002, INV-010, MDT-007, TRS-007 |  | open
EXE-004 | 146 | [EXECUTION] Implement the planning pipeline task | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | L |  | A | backend | Assigned | Nostidus4 | OPEN | EXE-003, CHR-002, ENG-008, POL-006, AGT-009, EXE-012 |  | open
EXE-005 | 60 | [EXECUTION] Build the signer service | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | L |  | A | backend | Assigned | Nostidus4 | OPEN | POL-006, POL-007, SC-016 |  | open
EXE-006 | 147 | [EXECUTION] Load the executor key from an encrypted keystore | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | EXE-005 |  | open
EXE-007 | 61 | [EXECUTION] Implement the executor with outbox semantics | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | EXE-005, EXE-001 |  | open
EXE-008 | 65 | [EXECUTION] Sequence steps with re-read and re-validation | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | EXE-007, CHR-003, POL-003, POL-007 |  | open
EXE-009 | 148 | [EXECUTION] Add the operator run-now endpoint | execution | [EPIC] M10 · Orchestration & Execution | P1 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | EXE-003 |  | open
EXE-010 | 149 | [EXECUTION] Track gas fees and alert on low executor gas | execution | [EPIC] M10 · Orchestration & Execution | P1 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | EXE-007 |  | open
EXE-011 | 150 | [EXECUTION] Execute the swap-for-gas step on the test router | execution | [EPIC] M10 · Orchestration & Execution | P2 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | EXE-008, SC-018 |  | open
EXE-012 | 249 | [EXECUTION] Implement the fee policy, fee holds and fee acceptance | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | MDT-001, CHR-001, ENG-001 |  | open
EXE-013 | 248 | [EXECUTION] Add the pause-only sentinel to the signer | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | EXE-005, EXE-006 |  | open
EXE-014 | 261 | [EXECUTION] Run the liquidity cycle (supply / withdraw) | execution | [EPIC] M10 · Orchestration & Execution | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | EXE-008, ENG-013, SC-024 |  | open
EXE-L01 | 151 | [EXECUTION] Add a KMS-backed signer | execution | [EPIC] M10 · Orchestration & Execution | — | Later | M |  | Later | backend | Accepted |  | OPEN | EXE-005 |  | open
EXE-L02 | 152 | [EXECUTION] Integrate the production swap adapter | execution | [EPIC] M10 · Orchestration & Execution | — | Later | M |  | Later | backend | Accepted |  | OPEN | EXE-011, SC-L03 |  | open
EXE-L03 | 153 | [EXECUTION] Add cross-chain bridging | execution | [EPIC] M10 · Orchestration & Execution | — | Later | L |  | Later | backend | Accepted |  | OPEN | TRS-L01 |  | open
EXE-L04 | 154 | [EXECUTION] Partition workers by treasury for scale | execution | [EPIC] M10 · Orchestration & Execution | — | Later | M |  | Later | backend | Accepted |  | OPEN | EXE-002 |  | open
IDN-001 | 32 | [IDENTITY] Create identity database schema and migrations | identity | [EPIC] M01 · Identity & Access | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | DEV-002 |  | open
IDN-002 | 37 | [IDENTITY] Implement magic-link login, sessions and CSRF | identity | [EPIC] M01 · Identity & Access | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | IDN-001 |  | open
IDN-003 | 105 | [IDENTITY] Rate-limit authentication endpoints | identity | [EPIC] M01 · Identity & Access | P0 | M1 | S |  | B | backend | Assigned | Nostidus4 | OPEN | IDN-002 |  | open
IDN-004 | 106 | [IDENTITY] Implement SIWE wallet linking | identity | [EPIC] M01 · Identity & Access | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | IDN-002 |  | open
IDN-005 | 38 | [IDENTITY] Implement organization creation and onboarding checklist | identity | [EPIC] M01 · Identity & Access | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | IDN-002 |  | open
IDN-006 | 39 | [IDENTITY] Implement RBAC dependencies and tenant isolation | identity | [EPIC] M01 · Identity & Access | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | IDN-005 |  | open
IDN-007 | 107 | [IDENTITY] Implement invites and membership management | identity | [EPIC] M01 · Identity & Access | P1 | M1 | M |  | After submission | backend | Assigned | Nostidus4 | OPEN | IDN-006 |  | open
IDN-008 | 108 | [IDENTITY] Implement the maker-checker service and solo mode | identity | [EPIC] M01 · Identity & Access | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | IDN-006 |  | open
IDN-L01 | 109 | [IDENTITY] Add MFA and step-up authentication | identity | [EPIC] M01 · Identity & Access | — | Later | L |  | Later | backend | Accepted |  | OPEN | IDN-002 |  | open
IDN-L02 | 110 | [IDENTITY] Add OIDC single sign-on | identity | [EPIC] M01 · Identity & Access | — | Later | L |  | Later | backend | Accepted |  | OPEN | IDN-006 |  | open
IDN-L03 | 111 | [IDENTITY] Add SAML and SCIM provisioning | identity | [EPIC] M01 · Identity & Access | — | Later | L |  | Later | backend | Accepted |  | OPEN | IDN-L02 |  | open
INV-001 | 45 | [INVOICES] Create invoice and request schema | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | MDT-001 |  | open
INV-002 | 49 | [INVOICES] Implement the request state machine | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | INV-001 |  | open
INV-003 | 52 | [INVOICES] Implement manual request creation and editing | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | INV-002, MDT-004 |  | open
INV-004 | 128 | [INVOICES] Implement document upload to private storage | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | INV-003 |  | open
INV-005 | 129 | [INVOICES] Implement CSV bulk import | invoices | [EPIC] M05 · Invoices & Payment Requests | P1 | M1 | M |  | After submission | backend | Assigned | Nostidus4 | OPEN | INV-003 |  | open
INV-006 | 119 | [INVOICES] Compute fingerprints at intake and block duplicates | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | INV-003, ENG-009 |  | open
INV-007 | 120 | [INVOICES] Implement deterministic anomaly checks | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | INV-006 |  | open
INV-008 | 121 | [INVOICES] Implement payment-terms confirmation | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | INV-003, ENG-005 |  | open
INV-009 | 122 | [INVOICES] Implement submit-for-approval and flag acknowledgment | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | INV-007, INV-008 |  | open
INV-010 | 123 | [INVOICES] Implement approval typed data and signature verification | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | INV-009, ENG-010, IDN-008 |  | open
INV-011 | 130 | [INVOICES] Implement reject, cancel, invalidation and expiry | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | S |  | B | backend | Assigned | Nostidus4 | OPEN | INV-010, SC-022, MDT-009 |  | open
INV-012 | 246 | [INVOICES] Detect near-duplicate requests | invoices | [EPIC] M05 · Invoices & Payment Requests | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | INV-006 |  | open
INV-L01 | 136 | [INVOICES] Add the email-forwarding invoice inbox | invoices | [EPIC] M05 · Invoices & Payment Requests | — | Later | L |  | Later | backend | Accepted |  | OPEN | INV-004, AGT-004 |  | open
INV-L02 | 137 | [INVOICES] Add the inbound invoice API with scoped keys | invoices | [EPIC] M05 · Invoices & Payment Requests | — | Later | M |  | Later | backend | Accepted |  | OPEN | INV-003 |  | open
INV-L03 | 138 | [INVOICES] Add recurring payment schedules | invoices | [EPIC] M05 · Invoices & Payment Requests | — | Later | M |  | Later | backend | Accepted |  | OPEN | INV-003 |  | open
INV-L04 | 139 | [INVOICES] Support fiat-denominated invoices | invoices | [EPIC] M05 · Invoices & Payment Requests | — | Later | L |  | Later | backend | Accepted |  | OPEN | INV-003, ENG-L02 |  | open
MDT-001 | 41 | [MANDATE] Create mandate, payee and exception schema | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | TRS-001 |  | open
MDT-002 | 43 | [MANDATE] Validate mandate drafts and generate summary and diff | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | MDT-001, ENG-001 |  | open
MDT-003 | 48 | [MANDATE] Implement mandate activation and read-back | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | MDT-002, MDT-009, TRS-006, CHR-003 |  | open
MDT-004 | 51 | [MANDATE] Implement vendor and payee proposals with screening | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | MDT-001, CMP-001 |  | open
MDT-005 | 118 | [MANDATE] Build payee registration and deactivation transactions and sync status | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P0 | M1 | M |  | B | backend | Assigned | Nostidus4 | OPEN | MDT-004, MDT-009, CHR-005 |  | open
MDT-006 | 124 | [MANDATE] Implement one-time exception requests and owner grant transactions | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P1 | M1 | M |  | B | backend | Assigned | Nostidus4 | OPEN | MDT-003, MDT-009, INV-010 |  | open
MDT-007 | 125 | [MANDATE] Implement pause and resume (backend and transactions) | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | MDT-003, MDT-009, EXE-013 |  | open
MDT-008 | 126 | [MANDATE] Sync mandate expiry and status | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P1 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | MDT-003 |  | open
MDT-009 | 247 | [MANDATE] Build governance transactions and collect owner signatures in the app | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P0 | M1 | L |  | A | backend | Assigned | Nostidus4 | OPEN | MDT-001, TRS-005 |  | open
MDT-010 | 251 | [MANDATE] Set up the Guardian Safe with the sentinel | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | MDT-009, EXE-013, TRS-006 |  | open
MDT-011 | 265 | [MANDATE] Add owner borrow/repay authorizations (governance) | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | P2 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | MDT-009, SC-026 |  | open
MDT-L01 | 127 | [MANDATE] Configure threshold-based approval policies | mandate | [EPIC] M03 · Mandate, Payees, Exceptions & Pause | — | Later | M |  | Later | backend | Accepted |  | OPEN | MDT-002, SC-L02 |  | open
NTF-001 | 184 | [NOTIFY] Create the domain event bus and notification routing | notifications | [EPIC] M13 · Notifications | P1 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | INV-002 |  | open
NTF-002 | 185 | [NOTIFY] Expose in-app notifications and the SSE stream | notifications | [EPIC] M13 · Notifications | P1 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | NTF-001 |  | open
NTF-003 | 186 | [NOTIFY] Add Telegram linking and delivery | notifications | [EPIC] M13 · Notifications | P2 | M1 | M |  | After submission | backend | Assigned | Nostidus4 | OPEN | NTF-001 |  | open
NTF-L01 | 187 | [NOTIFY] Add email notifications and digests | notifications | [EPIC] M13 · Notifications | — | Later | M |  | Later | backend | Accepted |  | OPEN | NTF-001 |  | open
NTF-L02 | 188 | [NOTIFY] Add outbound webhooks | notifications | [EPIC] M13 · Notifications | — | Later | M |  | Later | backend | Accepted |  | OPEN | NTF-001 |  | open
NTF-L03 | 189 | [NOTIFY] Add Slack, Lark and WeCom channels | notifications | [EPIC] M13 · Notifications | — | Later | L |  | Later | backend | Accepted |  | OPEN | NTF-001 |  | open
NTF-L04 | 190 | [NOTIFY] Add notification preferences | notifications | [EPIC] M13 · Notifications | — | Later | S |  | Later | backend | Accepted |  | OPEN | NTF-002 |  | open
OBS-001 | 200 | [OBSERVABILITY] Configure structured logging with correlation ids | observability | [EPIC] M17 · Observability & Analytics | P1 | M1 | S |  | After submission | infrastructure | Assigned | therealtunguyen | OPEN | CMP-003 |  | open
OBS-002 | 201 | [OBSERVABILITY] Add OpenTelemetry tracing | observability | [EPIC] M17 · Observability & Analytics | P1 | M1 | M |  | After submission | infrastructure | Assigned | therealtunguyen | OPEN | OBS-001 |  | open
OBS-003 | 202 | [OBSERVABILITY] Add Sentry and Prometheus metrics | observability | [EPIC] M17 · Observability & Analytics | P1 | M1 | S |  | After submission | infrastructure | Assigned | therealtunguyen | OPEN | OBS-001 |  | open
OBS-004 | 203 | [OBSERVABILITY] Compute operational metrics | observability | [EPIC] M17 · Observability & Analytics | P1 | M1 | M |  | After submission | infrastructure | Assigned | therealtunguyen | OPEN | AUD-001, EXE-008 |  | open
OBS-005 | 204 | [OBSERVABILITY] Compute the savings report | observability | [EPIC] M17 · Observability & Analytics | P1 | M1 | M |  | After submission | infrastructure | Assigned | therealtunguyen | OPEN | OBS-004, ENG-006 |  | open
POL-001 | 62 | [POLICY] Define the reason-code catalogue and decision model | policy-engine | [EPIC] M08 · Policy Engine & Attestation | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-001 |  | open
POL-002 | 63 | [POLICY] Validate approval, mandate and payee conditions | policy-engine | [EPIC] M08 · Policy Engine & Attestation | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | POL-001, ENG-010 |  | open
POL-003 | 64 | [POLICY] Validate limits, buffers, deadlines, coverage and unknown operations | policy-engine | [EPIC] M08 · Policy Engine & Attestation | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | POL-002 |  | open
POL-004 | 104 | [POLICY] Add differential tests between validator and contract | policy-engine | [EPIC] M08 · Policy Engine & Attestation | P0 | M1 | M |  | After submission | backend | Assigned | Nostidus4 | OPEN | POL-003, SC-013 |  | open
POL-005 | 58 | [POLICY] Define canonical plan encoding and planHash | policy-engine | [EPIC] M08 · Policy Engine & Attestation | P1 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | ENG-010 |  | open
POL-006 | 59 | [POLICY] Sign and verify EIP-712 plan attestations with the policy key | policy-engine | [EPIC] M08 · Policy Engine & Attestation | P1 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | POL-005 |  | open
POL-007 | 244 | [POLICY] Simulate each step with eth_call before signing | policy-engine | [EPIC] M08 · Policy Engine & Attestation | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | POL-003, POL-001, CHR-002, SC-016 |  | open
RCV-001 | 163 | [RECOVERY] Scan in-flight operations at startup | recovery | [EPIC] M12 · Recovery & Exceptions | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | EXE-007 |  | open
RCV-002 | 164 | [RECOVERY] Resolve unknown operations from chain evidence | recovery | [EPIC] M12 · Recovery & Exceptions | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | RCV-001, CHR-003 |  | open
RCV-003 | 165 | [RECOVERY] Handle partial completion and resume | recovery | [EPIC] M12 · Recovery & Exceptions | P0 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | EXE-008 |  | open
RCV-004 | 166 | [RECOVERY] Implement the review queue and routing | recovery | [EPIC] M12 · Recovery & Exceptions | P0 | M1 | M |  | B | backend | Assigned | Nostidus4 | OPEN | INV-002 |  | open
RCV-005 | 167 | [RECOVERY] Implement retry policy and error classification | recovery | [EPIC] M12 · Recovery & Exceptions | P0 | M1 | S |  | B | backend | Assigned | Nostidus4 | OPEN | EXE-007 |  | open
RCV-006 | 168 | [RECOVERY] Implement circuit-breaker rules and auto-pause | recovery | [EPIC] M12 · Recovery & Exceptions | P2 | M1 | M |  | After submission | backend | Assigned | Nostidus4 | OPEN | REC-001, MDT-007, EXE-013, CHR-006 |  | open
RCV-007 | 169 | [RECOVERY] Automate the crash-recovery test | recovery | [EPIC] M12 · Recovery & Exceptions | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | RCV-002 |  | open
REC-001 | 155 | [RECON] Verify post-conditions after each confirmed step | reconciliation | [EPIC] M11 · Verification & Reconciliation | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | EXE-008 |  | open
REC-002 | 156 | [RECON] Build reconciliation records with classification | reconciliation | [EPIC] M11 · Verification & Reconciliation | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | REC-001 |  | open
REC-003 | 157 | [RECON] Implement match, discrepancy and auto-match | reconciliation | [EPIC] M11 · Verification & Reconciliation | P0 | M1 | S |  | B | backend | Assigned | Nostidus4 | OPEN | REC-002 |  | open
REC-004 | 158 | [RECON] Export reconciliation CSV and journal lines | reconciliation | [EPIC] M11 · Verification & Reconciliation | P1 | M1 | M |  | B | backend | Assigned | Nostidus4 | OPEN | REC-003 |  | open
REC-005 | 159 | [RECON] Publish on-chain payment attestations | reconciliation | [EPIC] M11 · Verification & Reconciliation | P1 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | REC-002, SC-019 |  | open
REC-L01 | 160 | [RECON] Build the ERP integration framework with Xero | reconciliation | [EPIC] M11 · Verification & Reconciliation | — | Later | L |  | Later | backend | Accepted |  | OPEN | REC-004 |  | open
REC-L02 | 161 | [RECON] Add the QuickBooks connector | reconciliation | [EPIC] M11 · Verification & Reconciliation | — | Later | M |  | Later | backend | Accepted |  | OPEN | REC-L01 |  | open
REC-L03 | 162 | [RECON] Add the NetSuite connector | reconciliation | [EPIC] M11 · Verification & Reconciliation | — | Later | M |  | Later | backend | Accepted |  | OPEN | REC-L01 |  | open
SC-001 | 24 | [CONTRACTS] Set up the Foundry project with pinned dependencies | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Done |  | CLOSED | DEV-001 |  | open
SC-002 | 28 | [CONTRACTS] Define module storage, structs, EIP-712 domain, errors and events | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-001 |  | open
SC-003 | 29 | [CONTRACTS] Implement mandate governance and versioning | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-021 |  | open
SC-004 | 73 | [CONTRACTS] Implement the payee registry with cooling period | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-003 |  | open
SC-005 | 55 | [CONTRACTS] Implement approval signature verification | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-002 |  | open
SC-006 | 74 | [CONTRACTS] Implement pay() core flow | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-004, SC-005 |  | open
SC-007 | 75 | [CONTRACTS] Implement per-request limits and UTC daily counters | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-006 |  | open
SC-008 | 76 | [CONTRACTS] Enforce minimum buffers on pay and refill | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-006 |  | open
SC-009 | 77 | [CONTRACTS] Implement refill() bound to an approved request | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-005, SC-007, SC-008 |  | open
SC-010 | 30 | [CONTRACTS] Implement pause, resume, revoke and guardian | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-003 |  | open
SC-011 | 78 | [CONTRACTS] Implement one-time exceptions via owner governance | contracts | [EPIC] M04 · Smart Contracts | P1 | M1 | M |  | B | contracts | Assigned | longhuynh55 | OPEN | SC-007 |  | open
SC-012 | 79 | [CONTRACTS] Add the duplicate-invoice fingerprint registry and owner override | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-006 |  | open
SC-013 | 80 | [CONTRACTS] Write the contract acceptance test suite (AT cases) | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-009, SC-010, SC-012 |  | open
SC-014 | 81 | [CONTRACTS] Write the invariant and fuzz suite | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-013, SC-022 |  | open
SC-015 | 82 | [CONTRACTS] Run static analysis and write the findings report | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-013 |  | open
SC-016 | 31 | [CONTRACTS] Write deployment scripts and the deployments manifest | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-010, SC-021, DOM-001 |  | open
SC-017 | 56 | [CONTRACTS] Publish EIP-712 golden vectors | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-005 |  | open
SC-018 | 83 | [CONTRACTS] Add the test router and swapForGas | contracts | [EPIC] M04 · Smart Contracts | P2 | M1 | M |  | After submission | contracts | Assigned | longhuynh55 | OPEN | SC-009 |  | open
SC-019 | 84 | [CONTRACTS] Register the attestation schema and add an attest helper | contracts | [EPIC] M04 · Smart Contracts | P1 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | DOM-001 |  | open
SC-020 | 85 | [CONTRACTS] Write direct-call bypass tests | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-013 |  | open
SC-021 | 242 | [CONTRACTS] Implement the module factory with EIP-1167 clones | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-002 |  | open
SC-022 | 245 | [CONTRACTS] Add on-chain request cancellation | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-006, SC-009 |  | open
SC-023 | 255 | [CONTRACTS] Add two-option payment approvals (early / standard) | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-006, SC-005 |  | open
SC-024 | 256 | [CONTRACTS] Implement Aave V3 supply and withdraw through Safe T | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | M |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-021, SC-007, SC-008 |  | open
SC-025 | 257 | [CONTRACTS] Add Aave integration tests on a pinned Sepolia fork | contracts | [EPIC] M04 · Smart Contracts | P0 | M1 | S |  | A | contracts | Assigned | longhuynh55 | OPEN | SC-024, SC-016 |  | open
SC-026 | 258 | [CONTRACTS] Implement owner-authorized borrow and repay | contracts | [EPIC] M04 · Smart Contracts | P2 | M1 | M |  | After submission | contracts | Assigned | longhuynh55 | OPEN | SC-024 |  | open
SC-L01 | 86 | [CONTRACTS] Enforce reserves and execution holds on-chain | contracts | [EPIC] M04 · Smart Contracts | — | Later | L |  | Later | contracts | Accepted |  | OPEN | SC-014 |  | open
SC-L02 | 87 | [CONTRACTS] Enforce n-of-m approval thresholds by amount band | contracts | [EPIC] M04 · Smart Contracts | — | Later | L |  | Later | contracts | Accepted |  | OPEN | SC-005 |  | open
SC-L03 | 88 | [CONTRACTS] Add a production swap adapter with signed quotes | contracts | [EPIC] M04 · Smart Contracts | — | Later | L |  | Later | contracts | Accepted |  | OPEN | SC-018 |  | open
SC-L04 | 89 | [CONTRACTS] Verify plan attestations on-chain | contracts | [EPIC] M04 · Smart Contracts | — | Later | M |  | Later | contracts | Accepted |  | OPEN | SC-017 |  | open
SC-L05 | 90 | [CONTRACTS] Support multiple stablecoins with per-asset limits | contracts | [EPIC] M04 · Smart Contracts | — | Later | M |  | Later | contracts | Accepted |  | OPEN | SC-007 |  | open
SC-L06 | 91 | [CONTRACTS] Allow refill paths between operational wallets | contracts | [EPIC] M04 · Smart Contracts | — | Later | M |  | Later | contracts | Accepted |  | OPEN | SC-009 |  | open
TRS-001 | 33 | [TREASURY] Create treasury and chain schema | treasury | [EPIC] M02 · Treasury & Chain Configuration | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | IDN-001 |  | open
TRS-002 | 34 | [TREASURY] Load and validate platform chain configuration | treasury | [EPIC] M02 · Treasury & Chain Configuration | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | TRS-001 |  | open
TRS-003 | 36 | [TREASURY] Implement the asset registry with on-chain decimals check | treasury | [EPIC] M02 · Treasury & Chain Configuration | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | TRS-002, CHR-001 |  | open
TRS-004 | 40 | [TREASURY] Implement treasury creation with Safe verification | treasury | [EPIC] M02 · Treasury & Chain Configuration | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | TRS-003, IDN-006 |  | open
TRS-005 | 112 | [TREASURY] Read and snapshot Safe configuration | treasury | [EPIC] M02 · Treasury & Chain Configuration | P0 | M1 | S |  | A | backend | Assigned | Nostidus4 | OPEN | TRS-004 |  | open
TRS-006 | 44 | [TREASURY] Build the module deploy-and-enable Safe transaction | treasury | [EPIC] M02 · Treasury & Chain Configuration | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | TRS-004, SC-016, SC-021, MDT-009 |  | open
TRS-007 | 113 | [TREASURY] Compute coverage and handle acknowledgment | treasury | [EPIC] M02 · Treasury & Chain Configuration | P0 | M1 | M |  | A | backend | Assigned | Nostidus4 | OPEN | TRS-005, TRS-006 |  | open
TRS-008 | 114 | [TREASURY] Build a Safe deployment transaction from the UI | treasury | [EPIC] M02 · Treasury & Chain Configuration | P2 | M1 | S |  | After submission | backend | Assigned | Nostidus4 | OPEN | TRS-004 |  | open
TRS-L01 | 115 | [TREASURY] Support multiple treasuries with a consolidated view | treasury | [EPIC] M02 · Treasury & Chain Configuration | — | Later | M |  | Later | backend | Accepted |  | OPEN | TRS-004 |  | open
TRS-L02 | 116 | [TREASURY] Support multiple stablecoins per treasury | treasury | [EPIC] M02 · Treasury & Chain Configuration | — | Later | M |  | Later | backend | Accepted |  | OPEN | TRS-L01, SC-L05 |  | open
WEB-001 | 26 | [WEB] Create the web app shell | web | [EPIC] M16 · Web Application | P0 | M1 | M |  | A | frontend | Done |  | CLOSED | DEV-001 |  | open
WEB-002 | 208 | [WEB] Build login, org selection and onboarding checklist | web | [EPIC] M16 · Web Application | P0 | M1 | M |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-001, IDN-005 |  | open
WEB-003 | 209 | [WEB] Add wallet connection and SIWE linking | web | [EPIC] M16 · Web Application | P0 | M1 | S |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-002, IDN-004 |  | open
WEB-004 | 210 | [WEB] Build the treasury setup wizard | web | [EPIC] M16 · Web Application | P0 | M1 | M |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-003, TRS-007, WEB-025 |  | open
WEB-005 | 211 | [WEB] Build the mandate editor with summary, diff and activation | web | [EPIC] M16 · Web Application | P0 | M1 | L |  | B | frontend | Assigned | Nostidus4 | OPEN | WEB-004, MDT-003, WEB-025 |  | open
WEB-006 | 212 | [WEB] Build the payee registry UI | web | [EPIC] M16 · Web Application | P0 | M1 | M |  | B | frontend | Assigned | Nostidus4 | OPEN | WEB-004, MDT-005, WEB-025 |  | open
WEB-007 | 213 | [WEB] Build the request list and manual entry form | web | [EPIC] M16 · Web Application | P0 | M1 | M |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-002, INV-003 |  | open
WEB-008 | 214 | [WEB] Build upload and extraction review | web | [EPIC] M16 · Web Application | P0 | M1 | L |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-007, AGT-005 |  | open
WEB-009 | 215 | [WEB] Build the approval inbox and EIP-712 signing | web | [EPIC] M16 · Web Application | P0 | M1 | L |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-008, INV-010 |  | open
WEB-010 | 216 | [WEB] Build the treasury dashboard | web | [EPIC] M16 · Web Application | P0 | M1 | M |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-004, CHR-002 |  | open
WEB-011 | 217 | [WEB] Build plan cards and the Why panel | web | [EPIC] M16 · Web Application | P0 | M1 | M |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-010, EXE-004 |  | open
WEB-012 | 218 | [WEB] Build the live execution timeline | web | [EPIC] M16 · Web Application | P0 | M1 | M |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-011, NTF-002 |  | open
WEB-013 | 219 | [WEB] Build the exception and review console | web | [EPIC] M16 · Web Application | P0 | M1 | L |  | B | frontend | Assigned | Nostidus4 | OPEN | WEB-011, RCV-004, MDT-006, WEB-025 |  | open
WEB-014 | 220 | [WEB] Build the reconciliation view and export | web | [EPIC] M16 · Web Application | P0 | M1 | M |  | B | frontend | Assigned | Nostidus4 | OPEN | WEB-010, REC-004 |  | open
WEB-015 | 221 | [WEB] Build the notifications center | web | [EPIC] M16 · Web Application | P1 | M1 | S |  | After submission | frontend | Assigned | Nostidus4 | OPEN | WEB-001, NTF-002 |  | open
WEB-016 | 222 | [WEB] Build the Copilot chat UI | web | [EPIC] M16 · Web Application | P1 | M1 | M |  | After submission | frontend | Assigned | Nostidus4 | OPEN | WEB-010, AGT-012 |  | open
WEB-017 | 223 | [WEB] Build members and roles administration | web | [EPIC] M16 · Web Application | P1 | M1 | M |  | After submission | frontend | Assigned | Nostidus4 | OPEN | WEB-002, IDN-007 |  | open
WEB-018 | 224 | [WEB] Build metrics and savings pages | web | [EPIC] M16 · Web Application | P1 | M1 | M |  | After submission | frontend | Assigned | Nostidus4 | OPEN | WEB-010, OBS-005 |  | open
WEB-019 | 225 | [WEB] Add pause and resume controls and status banners | web | [EPIC] M16 · Web Application | P0 | M1 | S |  | B | frontend | Assigned | Nostidus4 | OPEN | WEB-010, MDT-007 |  | open
WEB-020 | 226 | [WEB] Build the CSV import UI | web | [EPIC] M16 · Web Application | P1 | M1 | S |  | After submission | frontend | Assigned | Nostidus4 | OPEN | WEB-007, INV-005 |  | open
WEB-021 | 227 | [WEB] Build the runway forecast chart | web | [EPIC] M16 · Web Application | P2 | M1 | S |  | After submission | frontend | Assigned | Nostidus4 | OPEN | WEB-010, ENG-011 |  | open
WEB-022 | 228 | [WEB] Run the accessibility and responsive pass | web | [EPIC] M16 · Web Application | P1 | M1 | S |  | After submission | frontend | Assigned | Nostidus4 | OPEN | WEB-014 |  | open
WEB-023 | 229 | [WEB] Write the Playwright end-to-end happy path | web | [EPIC] M16 · Web Application | P1 | M1 | M |  | After submission | frontend | Assigned | Nostidus4 | OPEN | WEB-012 |  | open
WEB-024 | 252 | [WEB] Build the fee policy and fee acceptance UI | web | [EPIC] M16 · Web Application | P1 | M1 | S |  | B | frontend | Assigned | Nostidus4 | OPEN | WEB-010, EXE-012 |  | open
WEB-025 | 250 | [WEB] Build the governance signing inbox | web | [EPIC] M16 · Web Application | P0 | M1 | M |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-003, MDT-009 |  | open
WEB-026 | 262 | [WEB] Build the treasury position card | web | [EPIC] M16 · Web Application | P0 | M1 | S |  | A | frontend | Assigned | Nostidus4 | OPEN | WEB-010 |  | open
WEB-027 | 263 | [WEB] Build the borrow proposal view | web | [EPIC] M16 · Web Application | P1 | M1 | S |  | B | frontend | Assigned | Nostidus4 | OPEN | WEB-026, ENG-014 |  | open

## Module Progress
Module | Tickets | Done | In Progress | Review | Not started | % done (count) | Est. days | Est. days done | % done (effort) | Cut A tickets | Cut A done | % Cut A done
admin
agent
audit
chain-reader
compliance
contracts
devex
domain-evidence
execution
financial-engine
identity
invoices
mandate
notifications
observability
policy-engine
reconciliation
recovery
treasury
web
TOTAL

## Status Summary
Status | All tickets | Cut A | Cut B | M1 | Later
Draft
Needs Discussion
Ready for Review
Accepted
Ready for Assignment
Assigned
In Progress
Review
Done
TOTAL
Generated | 2026-10-11 19:03 | from GitHub Project | https://github.com/users/Nostidus4/projects/1

## Dependencies
Ticket | Blocked by | Ticket status | Blocker status | Blocking now?
ADM-L01 | IDN-006
ADM-L02 | OBS-004
ADM-L03 | ADM-L02
AGT-001 | EXE-002
AGT-002 | AGT-001
AGT-003 | AGT-001
AGT-004 | AGT-003
AGT-004 | AGT-002
AGT-004 | INV-004
AGT-005 | AGT-004
AGT-005 | ENG-005
AGT-006 | AGT-004
AGT-007 | CHR-002
AGT-007 | ENG-008
AGT-007 | POL-003
AGT-008 | AGT-007
AGT-009 | AGT-008
AGT-009 | ENG-008
AGT-010 | ENG-007
AGT-010 | POL-003
AGT-011 | AGT-001
AGT-011 | MDT-006
AGT-012 | AGT-007
AGT-013 | AGT-005
AGT-013 | DOM-004
AGT-014 | AGT-009
AGT-014 | ENG-006
AGT-014 | DOM-005
AGT-015 | AGT-006
AGT-015 | DOM-006
AGT-016 | AGT-012
AGT-016 | DOM-007
AGT-017 | AGT-001
AUD-001 | IDN-001
AUD-002 | AUD-001
AUD-003 | AUD-001
AUD-003 | EXE-008
AUD-004 | CHR-002
AUD-L01 | AUD-002
CHR-001 | TRS-002
CHR-002 | CHR-001
CHR-002 | TRS-004
CHR-003 | CHR-001
CHR-003 | EXE-001
CHR-004 | CHR-003
CHR-005 | CHR-001
CHR-005 | SC-016
CHR-006 | CHR-005
CHR-006 | EXE-001
CMP-001 | MDT-001
CMP-002 | CMP-001
CMP-002 | POL-003
CMP-003 | DEV-001
CMP-L01 | CMP-001
CMP-L02 | CMP-L01
CMP-L03 | CMP-003
CMP-L04 | CMP-L03
DEV-002 | DEV-001
DEV-003 | DEV-001
DEV-004 | SC-001
DEV-005 | WEB-001
DEV-006 | SC-016
DEV-006 | TRS-004
DEV-006 | MDT-003
DEV-006 | INV-003
DEV-007 | DEV-006
DEV-007 | AUD-003
DEV-008 | DEV-007
DEV-009 | DEV-007
DEV-010 | DEV-002
DEV-010 | DOM-001
DEV-010 | SC-016
DEV-011 | DEV-001
DEV-012 | SC-016
DEV-012 | DEV-003
DOM-002 | DOM-001
DOM-007 | DOM-005
DOM-011 | DOM-009
DOM-011 | SC-015
DOM-012 | DOM-011
DOM-013 | DOM-008
DOM-014 | DEV-008
ENG-001 | DEV-001
ENG-002 | ENG-001
ENG-003 | ENG-002
ENG-004 | ENG-003
ENG-005 | ENG-001
ENG-006 | ENG-003
ENG-006 | ENG-005
ENG-007 | ENG-006
ENG-007 | ENG-012
ENG-008 | ENG-007
ENG-009 | ENG-001
ENG-010 | SC-017
ENG-010 | ENG-001
ENG-011 | ENG-003
ENG-012 | ENG-006
ENG-013 | ENG-002
ENG-013 | ENG-005
ENG-014 | ENG-013
ENG-L01 | ENG-007
ENG-L01 | SC-L06
ENG-L02 | ENG-005
ENG-L03 | ENG-007
EXE-001 | INV-001
EXE-002 | DEV-002
EXE-003 | EXE-002
EXE-003 | INV-010
EXE-003 | MDT-007
EXE-003 | TRS-007
EXE-004 | EXE-003
EXE-004 | CHR-002
EXE-004 | ENG-008
EXE-004 | POL-006
EXE-004 | AGT-009
EXE-004 | EXE-012
EXE-005 | POL-006
EXE-005 | POL-007
EXE-005 | SC-016
EXE-006 | EXE-005
EXE-007 | EXE-005
EXE-007 | EXE-001
EXE-008 | EXE-007
EXE-008 | CHR-003
EXE-008 | POL-003
EXE-008 | POL-007
EXE-009 | EXE-003
EXE-010 | EXE-007
EXE-011 | EXE-008
EXE-011 | SC-018
EXE-012 | MDT-001
EXE-012 | CHR-001
EXE-012 | ENG-001
EXE-013 | EXE-005
EXE-013 | EXE-006
EXE-014 | EXE-008
EXE-014 | ENG-013
EXE-014 | SC-024
EXE-L01 | EXE-005
EXE-L02 | EXE-011
EXE-L02 | SC-L03
EXE-L03 | TRS-L01
EXE-L04 | EXE-002
IDN-001 | DEV-002
IDN-002 | IDN-001
IDN-003 | IDN-002
IDN-004 | IDN-002
IDN-005 | IDN-002
IDN-006 | IDN-005
IDN-007 | IDN-006
IDN-008 | IDN-006
IDN-L01 | IDN-002
IDN-L02 | IDN-006
IDN-L03 | IDN-L02
INV-001 | MDT-001
INV-002 | INV-001
INV-003 | INV-002
INV-003 | MDT-004
INV-004 | INV-003
INV-005 | INV-003
INV-006 | INV-003
INV-006 | ENG-009
INV-007 | INV-006
INV-008 | INV-003
INV-008 | ENG-005
INV-009 | INV-007
INV-009 | INV-008
INV-010 | INV-009
INV-010 | ENG-010
INV-010 | IDN-008
INV-011 | INV-010
INV-011 | SC-022
INV-011 | MDT-009
INV-012 | INV-006
INV-L01 | INV-004
INV-L01 | AGT-004
INV-L02 | INV-003
INV-L03 | INV-003
INV-L04 | INV-003
INV-L04 | ENG-L02
MDT-001 | TRS-001
MDT-002 | MDT-001
MDT-002 | ENG-001
MDT-003 | MDT-002
MDT-003 | MDT-009
MDT-003 | TRS-006
MDT-003 | CHR-003
MDT-004 | MDT-001
MDT-004 | CMP-001
MDT-005 | MDT-004
MDT-005 | MDT-009
MDT-005 | CHR-005
MDT-006 | MDT-003
MDT-006 | MDT-009
MDT-006 | INV-010
MDT-007 | MDT-003
MDT-007 | MDT-009
MDT-007 | EXE-013
MDT-008 | MDT-003
MDT-009 | MDT-001
MDT-009 | TRS-005
MDT-010 | MDT-009
MDT-010 | EXE-013
MDT-010 | TRS-006
MDT-011 | MDT-009
MDT-011 | SC-026
MDT-L01 | MDT-002
MDT-L01 | SC-L02
NTF-001 | INV-002
NTF-002 | NTF-001
NTF-003 | NTF-001
NTF-L01 | NTF-001
NTF-L02 | NTF-001
NTF-L03 | NTF-001
NTF-L04 | NTF-002
OBS-001 | CMP-003
OBS-002 | OBS-001
OBS-003 | OBS-001
OBS-004 | AUD-001
OBS-004 | EXE-008
OBS-005 | OBS-004
OBS-005 | ENG-006
POL-001 | ENG-001
POL-002 | POL-001
POL-002 | ENG-010
POL-003 | POL-002
POL-004 | POL-003
POL-004 | SC-013
POL-005 | ENG-010
POL-006 | POL-005
POL-007 | POL-003
POL-007 | POL-001
POL-007 | CHR-002
POL-007 | SC-016
RCV-001 | EXE-007
RCV-002 | RCV-001
RCV-002 | CHR-003
RCV-003 | EXE-008
RCV-004 | INV-002
RCV-005 | EXE-007
RCV-006 | REC-001
RCV-006 | MDT-007
RCV-006 | EXE-013
RCV-006 | CHR-006
RCV-007 | RCV-002
REC-001 | EXE-008
REC-002 | REC-001
REC-003 | REC-002
REC-004 | REC-003
REC-005 | REC-002
REC-005 | SC-019
REC-L01 | REC-004
REC-L02 | REC-L01
REC-L03 | REC-L01
SC-001 | DEV-001
SC-002 | SC-001
SC-003 | SC-021
SC-004 | SC-003
SC-005 | SC-002
SC-006 | SC-004
SC-006 | SC-005
SC-007 | SC-006
SC-008 | SC-006
SC-009 | SC-005
SC-009 | SC-007
SC-009 | SC-008
SC-010 | SC-003
SC-011 | SC-007
SC-012 | SC-006
SC-013 | SC-009
SC-013 | SC-010
SC-013 | SC-012
SC-014 | SC-013
SC-014 | SC-022
SC-015 | SC-013
SC-016 | SC-010
SC-016 | SC-021
SC-016 | DOM-001
SC-017 | SC-005
SC-018 | SC-009
SC-019 | DOM-001
SC-020 | SC-013
SC-021 | SC-002
SC-022 | SC-006
SC-022 | SC-009
SC-023 | SC-006
SC-023 | SC-005
SC-024 | SC-021
SC-024 | SC-007
SC-024 | SC-008
SC-025 | SC-024
SC-025 | SC-016
SC-026 | SC-024
SC-L01 | SC-014
SC-L02 | SC-005
SC-L03 | SC-018
SC-L04 | SC-017
SC-L05 | SC-007
SC-L06 | SC-009
TRS-001 | IDN-001
TRS-002 | TRS-001
TRS-003 | TRS-002
TRS-003 | CHR-001
TRS-004 | TRS-003
TRS-004 | IDN-006
TRS-005 | TRS-004
TRS-006 | TRS-004
TRS-006 | SC-016
TRS-006 | SC-021
TRS-006 | MDT-009
TRS-007 | TRS-005
TRS-007 | TRS-006
TRS-008 | TRS-004
TRS-L01 | TRS-004
TRS-L02 | TRS-L01
TRS-L02 | SC-L05
WEB-001 | DEV-001
WEB-002 | WEB-001
WEB-002 | IDN-005
WEB-003 | WEB-002
WEB-003 | IDN-004
WEB-004 | WEB-003
WEB-004 | TRS-007
WEB-004 | WEB-025
WEB-005 | WEB-004
WEB-005 | MDT-003
WEB-005 | WEB-025
WEB-006 | WEB-004
WEB-006 | MDT-005
WEB-006 | WEB-025
WEB-007 | WEB-002
WEB-007 | INV-003
WEB-008 | WEB-007
WEB-008 | AGT-005
WEB-009 | WEB-008
WEB-009 | INV-010
WEB-010 | WEB-004
WEB-010 | CHR-002
WEB-011 | WEB-010
WEB-011 | EXE-004
WEB-012 | WEB-011
WEB-012 | NTF-002
WEB-013 | WEB-011
WEB-013 | RCV-004
WEB-013 | MDT-006
WEB-013 | WEB-025
WEB-014 | WEB-010
WEB-014 | REC-004
WEB-015 | WEB-001
WEB-015 | NTF-002
WEB-016 | WEB-010
WEB-016 | AGT-012
WEB-017 | WEB-002
WEB-017 | IDN-007
WEB-018 | WEB-010
WEB-018 | OBS-005
WEB-019 | WEB-010
WEB-019 | MDT-007
WEB-020 | WEB-007
WEB-020 | INV-005
WEB-021 | WEB-010
WEB-021 | ENG-011
WEB-022 | WEB-014
WEB-023 | WEB-012
WEB-024 | WEB-010
WEB-024 | EXE-012
WEB-025 | WEB-003
WEB-025 | MDT-009
WEB-026 | WEB-010
WEB-027 | WEB-026
WEB-027 | ENG-014

## How to use
This workbook is a REPORT. GitHub (Project 'TreasuryPilot · Delivery') is the source of truth.
To refresh: uv run --with openpyxl python planning/tracker/build_tracker.py
Do not edit statuses here; change them in the GitHub Project, then rebuild.
Status (column L, Issues) has a dropdown only for quick what-if analysis; changes are not synced back.
Est. days: S = 0.5, M = 1, L = 2 (planning estimates; not re-estimated by developers).
Open blockers = number of tickets listed in 'Blocked by' whose status is not Done.
Cut: A = required for the submission demo, B = stretch, After submission / Later = planned after 20/10.